## Roadmap
horizon | target | lane | item | deliverable | dependency | effort | owner | status | exit_criteria_link
v1.0 | 2026-06-23 | Clinical Safety | CDS Hooks expansion | Add order-select and medication-prescribe hooks with RxNorm bindings; integration tests against existing prescriptions module | â€” | M | Backend | completed | #h1.exit
v1.0 | 2026-06-23 | Clinical Safety | Drug-drug interaction check | Extend hms-medication-allergy-check to fire on coexisting prescriptions; warn-card on critical interactions | CDS Hooks expansion | M | Mixed (Backend + UI) | completed | #h1.exit
v1.0 | 2026-06-23 | Pharmacy | T-68 offline dispense queue | IndexedDB queue in pharmacy UI plus replay endpoint; covers hospitals with patchy connectivity | â€” | M | Mixed (Frontend + Backend) | not-started | #h1.exit
v1.0 | 2026-06-23 | Pharmacy | T-71 Playwright E2E | One end-to-end test per dispense path: Tier 1 in-house, Tier 2 partner, refill, AMU export | â€” | S | Frontend | not-started | #h1.exit
v1.0 | 2026-06-23 | Pharmacy | T-72 perf baseline | k6 script at 50 concurrent dispenses; p95 < 800ms; recorded in docs/observability/performance-baseline.md | â€” | S | Platform | not-started | #h1.exit
v1.0 | 2026-06-23 | Security | Idle session timeout (server-side) | Track last-activity in Redis; reject requests after 15 min idle; JWT silent refresh respects window | â€” | M | Backend | not-started | #h1.exit
v1.0 | 2026-06-23 | Security | Keycloak Phase C cutover | Flip OIDC_REQUIRED=true in UAT; soak 7 days; promote to prod; legacy /auth/login returns 410 Gone | Idle session timeout | S | Backend | not-started | #h1.exit
v1.0 | 2026-06-23 | Operations | DR runbook | docs/runbooks/disaster-recovery.md covering Railway snapshot+restore, Postgres PITR, observability stack rebuild | â€” | S | Platform | not-started | #h1.exit
v1.0 | 2026-06-23 | Accessibility | axe-core/playwright smoke | Fail PR on any new a11y violation across login, doctor dashboard, patient tracker, AVS | â€” | S | Frontend | not-started | #h1.exit
v1.0 | 2026-06-23 | Accessibility | Keyboard navigation pass | All clinical-flow screens reachable + actionable via keyboard; documented in docs/ui/accessibility.md | axe-core/playwright smoke | M | Frontend | not-started | #h1.exit
v1.0 | 2026-06-23 | i18n | FR completeness gate | Tooling extracts all *.json keys; CI fails when any locale is < 99% of EN; enforced in frontend-ci.yml | â€” | S | Frontend | started | #h1.exit
v1.0 | 2026-06-23 | Releases | v1.0.0-rc1 cut | Tag, signed release notes from CHANGELOG.md, freeze feat/* for 1 week, only fix/* allowed during soak | All v1.0 items | S | Platform | not-started | #h1.exit
v1.1 | 2026-10-01 | Interop FHIR | FHIR write API | POST/PUT for Patient, Encounter, Observation; conditional create via If-None-Exist; metadata updated to advertise write capabilities | FHIR read API (done) | L | Backend | not-started | #h2.exit
v1.1 | 2026-10-01 | Interop FHIR | FHIR Bulk Data Access ($export) | Bulk export for Patient and Group; output to S3-compatible bucket; documented in docs/fhir-bulk.md | FHIR write API | M | Backend | not-started | #h2.exit
v1.1 | 2026-10-01 | Interop FHIR | FHIR $everything operation | Patient compartment export; required by most HIE handshakes | FHIR write API | M | Backend | not-started | #h2.exit
v1.1 | 2026-10-01 | Interop HL7 | ORU^R01 â†’ LabResult persistence | Match by accession number; write to existing lab_result schema; link to encounter; integration tested with Mindray/Sysmex sample messages | HL7 MLLP listener (done) | M | Backend | not-started | #h2.exit
v1.1 | 2026-10-01 | Interop HL7 | ADT â†’ Admission/Encounter sync | ADT^A01/A04/A08 trigger Admission and Encounter sync; conflict-resolution rules documented | HL7 MLLP listener (done) | M | Backend | not-started | #h2.exit
v1.1 | 2026-10-01 | Patient Identity | EMPI v0 (intra-tenant) | Probabilistic match on name + DOB + sex + national-ID where present; candidate-match workflow in receptionist UI; â‰¥90% recall on labelled audit set | â€” | L | Mixed (Backend + Frontend) | not-started | #h2.exit
v1.1 | 2026-10-01 | Clinical Safety | CDS Hooks LOINC binding | Bind hms-patient-view problem cards to LOINC alongside existing ICD | CDS Hooks expansion (v1.0) | S | Backend | not-started | #h2.exit
v1.1 | 2026-10-01 | Clinical Safety | CDS Hooks public discovery | /api/cds-services validated against Cerner and Epic CDS Hooks sandbox | CDS Hooks expansion (v1.0) | S | Backend | not-started | #h2.exit
v1.1 | 2026-10-01 | Mobile | Patient mobile parity (Android) | Add Referrals, Treatments, Billing screens to Android app to match web portal capability | â€” | L | Mobile | not-started | #h2.exit
v1.1 | 2026-10-01 | Mobile | Patient mobile parity (iOS) | Add Referrals, Treatments, Billing screens to iOS app to match web portal capability | â€” | L | Mobile | not-started | #h2.exit
v1.1 | 2026-10-01 | Mobile | Push notifications for lab results | FCM/APNs already wired backend-side; add UI toggles + deep links to LabResultsDetail | Mobile parity | M | Mixed (Mobile + Backend) | not-started | #h2.exit
v1.1 | 2026-10-01 | Mobile | Mobile test coverage uplift | Bring per-app test count from 5 to 30+ (unit + UI snapshots); add Detox or Maestro for E2E | â€” | M | Mobile | not-started | #h2.exit
v1.1 | 2026-10-01 | Reporting | KPI dashboard service | Materialized views for avg door-to-doctor, dispense lead time, no-show rate; surfaced in existing analytics/ module | â€” | M | Mixed (Backend + Frontend) | not-started | #h2.exit
v2.0 | 2027-04-01 | Multi-tenancy | Schema-per-tenant migration path | Row-level multi-tenancy stays default; schema-per-tenant available for hospitals with strong isolation needs (military, private foreign) | â€” | XL | Mixed (Backend + Platform) | not-started | #h3.exit
v2.0 | 2027-04-01 | Multi-tenancy | Tenant onboarding pipeline | One-command provision: realm, schema, seed data, observability namespace, Splunk index | Schema-per-tenant migration path | L | Platform | not-started | #h3.exit
v2.0 | 2027-04-01 | Performance | Read replicas + Hikari tuning | Hikari pool sized to actual concurrent users; RO replica routing for FHIR reads and dashboards | â€” | M | Backend | not-started | #h3.exit
v2.0 | 2027-04-01 | Performance | Async dispense + lab via Kafka | Move ORU result + dispense settlement to Kafka consumers; reduce request-thread blocking | ORU^R01 persistence | L | Backend | not-started | #h3.exit
v2.0 | 2027-04-01 | Compliance | SOC 2 Type I â†’ Type II | Control map (existing audit logs/RBAC/encryption cover ~60% of CC1â€“CC9); gap analysis in docs/compliance/soc2-gap.md; 12-month observation window | â€” | XL | Mixed (Compliance + Backend) | not-started | #h3.exit
v2.0 | 2027-04-01 | Compliance | HIPAA-equivalent posture | BAA template; PHI inventory; key rotation; access review cadence â€” for international customers | â€” | L | Compliance | not-started | #h3.exit
v2.0 | 2027-04-01 | Compliance | ECOWAS data-residency support | Per-tenant region pinning (Railway â†’ AWS or OVH-Africa); required for Senegal/CÃ´te d'Ivoire/Ghana sales | â€” | L | Platform | not-started | #h3.exit
v2.0 | 2027-04-01 | Patient Identity | EMPI v1 (cross-tenant) | National-ID-keyed; explicit patient Consent resource per data-sharing event; FHIR Consent | EMPI v0 | L | Backend | not-started | #h3.exit
v2.0 | 2027-04-01 | Clinical Depth | OB/GYN + pediatrics finish | Complete the partially-designed HighRiskPregnancyCarePlan*, NewbornAssessment*, PostpartumCare* services and matching UI | â€” | L | Mixed (Backend + Frontend) | not-started | #h3.exit
v2.0 | 2027-04-01 | Clinical Depth | DICOM proxy | Extend existing imaging/ module with Orthanc or dcm4chee adapter for actual image viewing | â€” | L | Mixed (Backend + Frontend) | not-started | #h3.exit
v2.0 | 2027-04-01 | Operations | Synthetic monitoring | Grafana k6 cloud or Blackbox-exporter probes from 3 geos; alert on > 10% probe failure for 5 min | DR runbook | S | Platform | not-started | #h3.exit
v2.0 | 2027-04-01 | Operations | Per-tenant cost observability | Tag every Splunk event + Grafana series with tenant; chargeback report per hospital | Splunk HEC (done #276) | M | Platform | not-started | #h3.exit
oos | â€” | Out of scope | AI/LLM clinical features | Deferred â€” regulatorily risky in healthcare; no existing groundwork in repo. Revisit after v1.0 | â€” | â€” | â€” | deferred | â€”
oos | â€” | Out of scope | Splunk Observability Cloud (metrics) | Deferred â€” duplicates the OTelâ†’Grafana Cloud path landed in #276 | â€” | â€” | â€” | deferred | â€”
oos | â€” | Out of scope | Jenkins | Dropped â€” GitHub Actions already covers CI/CD; Jenkins would be parallel duplication | â€” | â€” | â€” | dropped | â€”
oos | â€” | Out of scope | Direct LDAP/Kerberos in hospital-core | Dropped â€” auth concerns belong in Keycloak; configure user federation there per deployment | â€” | â€” | â€” | dropped | â€”
oos | â€” | Out of scope | Revenue-cycle / claims module | Deferred â€” out of scope for clinical+pharmacy MVP; partner with a billing vendor instead | â€” | â€” | â€” | deferred | â€”